## Assignments
Employee | Role | Project | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03
Sarah Johnson | Senior Analyst | Financial System Migration | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Sarah Johnson | Senior Analyst | Compliance Review 2025 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0
Michael Chen | Project Manager | Security Audit Q3 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 0
Emily Davis | Lead Auditor | Financial System Migration | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
James Wilson | Security Specialist | Security Audit Q3 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0
James Wilson | Security Specialist | Network Security Implementation | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Maria Garcia | Data Analyst | Cloud Infrastructure Upgrade | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Maria Garcia | Data Analyst | Data Analytics Platform | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Robert Smith | Risk Manager | Financial System Migration | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Lisa Anderson | PM | Customer Portal Enhancement | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0
Lisa Anderson | PM | Process Automation Initiative | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
David Brown | Security Lead | Network Security Implementation | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Jennifer Taylor | Senior PM | Data Analytics Platform | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Jennifer Taylor | Senior PM | Database Modernization | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Thomas Martinez | Risk Analyst | Risk Assessment Framework | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Amanda White | Business Analyst | Process Automation Initiative | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Amanda White | Business Analyst | Customer Portal Enhancement | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0
Christopher Lee | Tech Lead | Database Modernization | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Christopher Lee | Tech Lead | Cloud Infrastructure Upgrade | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15

## Employees
ID | Name | Email | Team | Max Hours | Communication | Cybersecurity | Data Analysis | Financial Auditing | Project Management | Risk Assessment
EMP001 | Sarah Johnson | sarah.johnson@company.com | Operations | 40 | Advanced | Intermediate | Expert | Beginner | Advanced | Intermediate
EMP002 | Michael Chen | michael.chen@company.com | Finance | 40 | Expert | Advanced | Intermediate | None | Expert | Advanced
EMP003 | Emily Davis | emily.davis@company.com | Finance | 35 | Intermediate | Beginner | Advanced | Expert | Intermediate | Expert
EMP004 | James Wilson | james.wilson@company.com | IT | 40 | Beginner | Expert | Advanced | Intermediate | Advanced | Intermediate
EMP005 | Maria Garcia | maria.garcia@company.com | Finance | 40 | Advanced | Intermediate | Expert | Advanced | Beginner | Advanced
EMP006 | Robert Smith | robert.smith@company.com | Operations | 40 | Expert | None | Intermediate | Expert | Advanced | Expert
EMP007 | Lisa Anderson | lisa.anderson@company.com | IT | 35 | Intermediate | Advanced | Beginner | Intermediate | Expert | Intermediate
EMP008 | David Brown | david.brown@company.com | Analytics | 40 | Advanced | Expert | Advanced | None | Intermediate | Beginner
EMP009 | Jennifer Taylor | jennifer.taylor@company.com | Analytics | 40 | Expert | Intermediate | Expert | Advanced | Advanced | Advanced
EMP010 | Thomas Martinez | thomas.martinez@company.com | PMO | 40 | Intermediate | Advanced | Intermediate | Expert | Beginner | Expert
EMP011 | Amanda White | amanda.white@company.com | PMO | 35 | Advanced | Beginner | Advanced | Intermediate | Expert | Intermediate
EMP012 | Christopher Lee | christopher.lee@company.com | IT | 40 | Beginner | Expert | Expert | Beginner | Intermediate | Advanced

## Projects
ID | Name | Start Date | End Date | Portfolio | Required Skills
PROJ000 | Time Off | 2025-01-01 | 2025-12-31 | All | None
PROJ001 | Security Audit Q3 | 2025-09-01 | 2025-11-30 | IT Security | Cybersecurity, Risk Assessment, Data Analysis
PROJ002 | Financial System Migration | 2025-08-15 | 2025-12-15 | Finance | Financial Auditing, Data Analysis, Project Management
PROJ003 | Cloud Infrastructure Upgrade | 2025-09-01 | 2026-01-31 | IT Infrastructure | Data Analysis, Project Management, Risk Assessment
PROJ004 | Compliance Review 2025 | 2025-08-01 | 2025-10-31 | Compliance | Financial Auditing, Risk Assessment, Communication
PROJ005 | Data Analytics Platform | 2025-09-15 | 2026-02-28 | Digital Transformation | Data Analysis, Project Management, Communication
PROJ006 | Risk Assessment Framework | 2025-10-01 | 2026-03-31 | Risk Management | Risk Assessment, Financial Auditing, Communication
PROJ007 | Customer Portal Enhancement | 2025-08-01 | 2025-11-15 | Customer Experience | Project Management, Data Analysis, Communication
PROJ008 | Network Security Implementation | 2025-09-01 | 2025-12-31 | IT Security | Cybersecurity, Risk Assessment, Project Management
PROJ009 | Process Automation Initiative | 2025-08-15 | 2026-01-15 | Operations | Data Analysis, Project Management, Communication
PROJ010 | Database Modernization | 2025-10-01 | 2026-02-15 | IT Infrastructure | Data Analysis, Risk Assessment, Project Management